ENROLLMENT MANAGEMENT PLAN:

RECRUITMENT STRATEGIES

| RECRUITMENT STRATEGIES | LEAD & PARTICIPANTS | TIMELINE |
| --- | --- | --- |
| 1. Implement Inquiry Management System - Engage 60+ academic employees to cover discipline/program advising for potential students identified by the system - Increase # of applications to enrollment conversion yields. - Report on IMS conversion yield for fall 06 - Send frequent reminders, information and updates to prospective students thru IMS (PODCASTS) | Chris T., Jeff O-H, Campus Community | April 06 Oct. 06 & ongoing FA, WIN, SPR 06-07 Mid-August 06 |
| 2. Analyze Recruitment/Outreach and all other written communications for quality, effectiveness and tone. | Robin Y., Chris T., Chris M., Norma G., Susan H., A. Rye, Counselors, PIO | May/June 06 through FA Qtr. |
| 3. Develop and send recruitment materials and letter to all UW-Bothell applicants who were not accepted. - Coordinate Dual Enrollment promotion with U of W Bothell | Robin Y., Carla H., Susan H. Yvonne T-P & Student Services staff | May/June 06 |
| 4. Develop targeted information and welcome messages for specific racial/ethnic groups | Diversity & Student Success staff | SU, FA, WIN, SPR 06-07 |
| 5. Contact SPR 06 student “no shows” and encourage to register SU/FA 06. | Robin Y., Chris T., Chris M. & other Student Services staff | SPR, SU, FA 06 |
| RECRUITMENT STRATEGIES | LEAD & PARTICIPANTS | TIMELINE |
| 6. Improve campus visitation and tours - Tour training for Student Ambassadors and interested Staff. | Student Activities, Diversity & Student Success staff, | SPR, SU 06 FA 06 and ongoing |
| 7. Schedule 50+ faculty & staff presentations at high schools inside and outside of the district promoting specific programs, majors and college-wide attractions. | Jeff O-H, faculty & staff | FA 06 and ongoing |
| 8. Increase outreach efforts to 25 new community and workforce groups | Jeff O-H and Workforce staff | FA 06 |
| 9. Increase the number of Running Start students who complete an AAS degree at SCC before transferring. | Running Start, other Student Services staff and Instruction | FA 06, WIN & SPR 07 & ongoing |
| 10. Increase outreach efforts to 25 new community and workforce groups. | Jeff O-H and Workforce staff | FA 06 |
| 11. Increase outreach and recruitment to students of color. - peer support role | Diversity & Student Success staff, Running Start staff, Athletics | SPR 06 & ongoing |
| 12. Increase outreach and recruitment efforts to ABE/ESL populations. | Essential Skills, and Diversity and Student Success staff | FA 06 |
| 13. Add (1) additional IBEST Program | Berta L., Rebecca R., Deans, Essential Skills staff | WIN qtr. 07 |
| 14. Develop an Honors Program and recruit HS students into program. | Ken Lawson, IAS/SS faculty | FA qtr. 06 |
| RECRUITMENT STRATEGIES | LEAD & PARTICIPANTS | TIMELINE |
| 15. Summer Camp for music Students. | Music Faculty | SU 06 & 07 |
| 16. Coordinate w/ FA, Testing, A&C & ER for One-Stop Student Registration Service. | Robin Y, Ted H, Testing staff, Advising & Counseling staff | SU O6 FA O6 & ongoing |
| 17. Develop Business Incubator Program @ LFP | Business Admin. Faculty & LFP Staff | July 06 |

ENROLLMENT MANAGEMENT PLAN:

MARKETING STRATEGIES

| Marketing STRATEGIES | LEAD & PARTICIPANTS | TIMELINE |
| --- | --- | --- |
| 1. Review key communications with the general community - Class Schedule - Newsletter | PIO | SU 06 |
| 2. Create targeted publications for Global Studies, Business, Visual Arts & other areas of distinction | PIO | FA 06 |
| 3. Engage community & students in research efforts | PIO | Now through next year |
| 4. Develop PR Toolkit for faculty & staff that includes templates for flyers, posters, event organization, marketing plans | PIO | FA 06 |
| 5.. Utilize the web to “mirror” our communications to all targeted groups. Stay connected with all groups developing marketing materials. | PIO | Ongoing |
| 6. Inquiry Management System - Engage in communications audit of the IMS: Create e-materials & review current print materials | PIO | Ongoing |

ENROLLMENT MANAGEMENT PLAN:

RETENTION STRATEGIES

| RETENTION STRATEGIES | LEAD & PARTICIPANTS | TIMELINE |
| --- | --- | --- |
| 1. Contacts students who have not returned to college from the previous quarter | Robin Y., Enrollment Mgt. Staff, Admissions Staff & volunteers | FA 06, WIN 07, SPR 07 |
| 2. Contact students who submitted an application & those who registered but were no-shows | Robin Y., Chris T., other Enrollment Mgt. Staff, Admissions. Staff & volunteers | FA 06, WIN 07, SPR 07 |
| 3. Fully implement prerequisite checking for Math & English - Increase access to online registration | Norma G., Susan H., Enrollment Services, Academic Affairs | FA 06 & ongoing |
| 4. Advising Day | Advising & Counseling, Enrollment Services Staff and Instruction | FA 06 |
| 5. Advising Training | Yvonne T-P, A & C & Deans, Advising & Counseling & faculty | FA 06 |
| 6. Create Pre-major planning sheets for all majors | Deans & Divisions, Advising & Counseling | 50% complete by Dec. 06/remainder by June 07 |
| 7. Implement Grade Alert System/Early Warning System | Grade Alert Committee, Advising & Counseling, Student Services, Instruction | FA 06, WIN 07 & ongoing |
| 8. Identify high risk students as they enroll in the college. Apprise & introduce them to the academic skills resources & tutoring programs | Diversity & Student Success staff, Advising & Counseling, Instruction, Enrollment Services | FA 06, WIN 07 & ongoing |
| RETENTION STRATEGIES | LEAD & PARTICIPANTS | TIMELINE |
| 9. Create additional Student Interest Groups (SIG). | Advisig & Counseling, Essential Skills, Learning Centers staff | FA 06 & ongoing |
| 10. Use Diversity Action Framework & Noel-Levitz indicators to identify students more likely to be early leavers | Diversity and Student Success, Instruction, Enrollment Services, Advising & Counseling | FA 06 & ongoing |
| 11. Implement a “what you need to succeed” campaign to increase retention - Establish contact & engage student participants in retention initiatives - Identify current students to serve in peer support role | Diversity and Student Success, and Advising & Counseling staff, Instruction | FA 06 & ongoing |
| 12. Continue offering SIG for athletes | Athletic Dept., English Dept. | FA 06 & ongoing |
| 13. Offer tips to staff for helping students get to needed resources & encourage follow-up | Diversity and Student Success staff, and & Advising & Counseling | FA 06 & ongoing |
| 14. Review & revise quarterly class schedule to alleviate conflicts & barriers. Coordinate the distribution of course offerings across departments & programs. - Develop an annual schedule - Offer sufficient numbers & levels of Math & English courses based on placement test scores of students as reported in the Testing Center | Instruction & Student Services Instruction & Student Services Humanities & Math/Science | FA 06 & ongoing FA 06 & ongoing FA 06 & ongoing |