1800 Building Move Out Schedule

March/April 2009

Preparing for Construction – Steps Needed to Empty Out the Building

NOTE:  Please remember that starting early on some of these items is perfectly fine if there is no disruption and/or negative effect on Winter Quarter classes.  If boxes are needed, please contact Bob Roehl via e-mail or phone message (x4514).

| Start Date | End Date | Room(s) | Action Required |  |  |  |  |  |  |  | Completion Responsibility |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3/16/09 | 3/20/09 | All 8 Classrooms | Faculty User Leads (bolded) for each classroom are asked to inform Arlene Strong at x4540 about what personal items need to be moved, from what classroom, and where they will be stored. Box up and label all personal items that require it ASAP. |  |  |  |  |  |  |  | Bob Roehl/Facilities Faculty Users List Arlene Strong |
|  |  |  | 1801 | 1802 | 1803 | 1805 | 1811 | 1812 | 1813 | 1814 |  |
|  |  |  | G Henry | R David | P Herrick | L Warren | P-Gladst | T Payne | T Taylor | R Jacobs |  |
|  |  |  | Culbertson | Slusher | N McNeill | L Clarke | D Holz | S Ku | L Fuell | L Clarke |  |
|  |  |  |  | Hayden |  | Slusher | B Yasui | Christensen | P Sparks | A Winters |  |
|  |  |  |  | E Johnson |  |  | Muskett |  |  |  |  |
| 3/16/09 | 3/27/09 | All 8 Classrooms | Faculty Leads, Arlene Strong, and Bob Roehl will coordinate activities needed to get all personal items moved and stored properly. |  |  |  |  |  |  |  |  |
| 3/16/09 | 3/20/09 | Racquetball Court | Purchase and lay down tarps to protect the floor before items brought in for storage. |  |  |  |  |  |  |  | Ron Norimatsu |
| 3/23/09 | 3/24/09 | All 8 Classrooms | Label each item with its classroom number. This includes tables, chairs, whiteboards, media and computer equipment, etc. |  |  |  |  |  |  |  | Bob Roehl/Larry Cheng/Gary Kalbfleisch |
| 3/23/09 | 3/27/09 | All 8 Classrooms | Remove and store all media equipment. This includes projectors, projector cages, speakers, overhead projectors, media towers, and projector screens to be salvaged. |  |  |  |  |  |  |  | Larry Cheng/Paul Fernandez/Ron Norimatsu |
| 3/23/09 | 3/27/09 | All 8 Classrooms | Remove and store all computer related equipment (data closets) |  |  |  |  |  |  |  | Gary Kalbfleisch/TSS |
| 3/23/09 | 3/27/09 | Items from 1800 most suited for temporary classrooms | Set up two temporary classrooms in the FOSS Building. They are Room 5101 (old Bookstore) and Room 5100 (old Student Lounge). Also, set up PUB conference rooms as classrooms. Furniture and equipment from the 1800 Building will be used as needed, along with items purchased by Larry Cheng that are needed to properly set them up as temporary classrooms. |  |  |  |  |  |  |  | Bob Roehl/Facilities Larry Cheng/Media |
| ----- | 3/27/09 | Outside 1802 | Remove coke machine. |  |  |  |  |  |  |  | Mary Kelemen/Aux. Services |
| 3/23/09 | 4/1/09 | All 8 Classrooms | Remove all wall items not specific to faculty users. Items include whiteboards. |  |  |  |  |  |  |  | Bob Roehl/Facilities |
| 3/23/09 | 4/1/09 | Mech. Room | Remove and store all loose items, including custodial items. |  |  |  |  |  |  |  | Bob Roehl/Facilities |
| 4/2/09 | 4/2/09 | All 8 Classrooms | Remove and store all tables, chairs, and remaining classroom items. |  |  |  |  |  |  |  | Hansen Bros./Facilities |

Storage Locations

All persons/groups responsible for the removal and storage of classroom items are requested to label each item and write down where they stored them.  This detailed information will be placed on the chart below so we can easily find everything when it becomes time to make the building and classrooms operational again.

| 1801 | 1802 | 1803 | 1805 | 1811 | 1812 | 1813 | 1814 | Description of Storage Item(s) | Storage Location |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | √ | √ | √ | √ | √ | √ |  | Media equipment rack, equipment inside rack, LCD cage, speakers | Hallway leading to Room 4215 (on top of or inside of rack) |
|  | √ | √ | √ | √ | √ | √ |  | LCD Projector | Locked Cabinet in Room 4215 |
|  | √ | √ | √ | √ | √ | √ |  | Overhead Cart/Projector | PUB and FOSS temporary classrooms |
| √ |  |  |  |  |  |  | √ | Overhead Cart/Projector | AV Storage Room |
| √ |  |  |  |  |  |  |  | Screen & wall mounted TV/DVD/VCR | Room 4215 |
|  |  |  |  |  |  |  | √ | Screen, VCR, DVD player, slide projector | Room 4215 |
|  |  |  |  |  |  |  | √ | Two wall mounted TVs, | ?? |
| √ | √ | √ | √ | √ | √ | √ | √ | Tables, desks, and chairs | 3000 Building Racquetball Court |
|  |  |  |  |  |  |  |  | Computer Equipment |  |
| √ | √ | √ | √ | √ | √ | √ | √ | Whiteboards | 3000 Building Racquetball Court |
|  |  |  |  |  |  | √ |  | Terry Taylor Wall Maps |  |
|  |  |  |  |  |  |  |  | Salvaged projector screens & low voltage switches | ?? |