**Timeline: Reorganization of Academic & Student Affairs**

* Review/Finalize Re-Org Plan with SET                                   By April 12
* Share Re-Org Plan with JUMC, UMCC, & Campus              April 15-16
* Submit updated PDFs to HR                                                     April 17
* Collect Campus Input                                                         April 15 – May 3
* Screening Committee Meeting                                 By May 3
* External Recruitment Application Period                               May 6 – June 5
* Committee Review of Applications                                         June 10– 13
* Candidates Selected for Interview                                           June 14
* Interviews                                                                                     June 24 – 28
* Finalist Selected                                          By July 8

The following administrative **PDFs submitted to HR** by Friday, April 19:

* Dean, Learning Technologies & Academic Resources
* Dean, Liberal Arts
* Dean, Workforce/Continuing Education/Transitional Studies

The following classified **PDFs submitted** (following discussion with area supervisors):

* Administrative Assistant, Liberal Arts
* Secretary Senior, Learning Technologies & Academic Resources